## Sheet1 (2)
S/N | Module | Submodule | Service | Actions | Start | End | Status | Resource | Figma
1 | Sales | Customer | Customer Service | List View | 2025-02-01 | 2025-02-01 | Completed | Agu
|  |  |  | Create Single | 2025-02-02 | 2025-02-02 | Completed | Agu
|  |  |  | Update Single | 2025-02-03 | 2025-02-03 | Pending | Agu
|  |  |  | View Profile | 2025-02-04 | 2025-02-04 | Review | Agu
|  |  |  | Reassign Agent | 2025-02-05 | 2025-02-05 | Pending | Agu
|  |  |  | Brands | 2025-02-06 | 2025-02-06 | Pending | Agu
|  |  |  | Location | 2025-02-07 | 2025-02-07 | Pending | Agu
|  |  |  | Sub contact | 2025-02-08 | 2025-02-08 | Pending | Agu
|  |  |  | Deactivate | 2025-02-09 | 2025-02-09 | Pending | Agu
|  | Orders | Order Service | List View | 2025-02-11 | 2025-02-11 | In Progress | Agu
[5 empty] | 2025-02-12 | 2025-02-12
[5 empty] | 2025-02-13 | 2025-02-13
[5 empty] | 2025-02-14 | 2025-02-14
[5 empty] | 2025-02-15 | 2025-02-15
[5 empty] | 2025-02-16 | 2025-02-16
|  | Inventory | Inventory |  | 2025-02-17 | 2025-02-17
[5 empty] | 2025-02-18 | 2025-02-18
[5 empty] | 2025-02-19 | 2025-02-19
[5 empty] | 2025-02-20 | 2025-02-20
|  | Productivity Tracker | Beat Plan | List | 2025-02-21 | 2025-02-21 | Review | Howard
|  |  |  | Create | 2025-02-22 | 2025-02-22 | Review | Howard
|  |  |  | View Details | 2025-02-23 | 2025-02-23 | In Progress | Howard
[5 empty] | 2025-02-24 | 2025-02-24
|  |  | Targets | List | 2025-02-25 | 2025-02-25 | In Progress | Blessing
|  |  |  | Create | 2025-02-26 | 2025-02-26 | In Progress | Blessing
|  |  |  | View Details | 2025-02-27 | 2025-02-27 | In Progress | Blessing
[5 empty] | 2025-02-28 | 2025-02-28
|  |  | Map Overlay | View | 2025-03-01 | 2025-03-01
[5 empty] | 2025-03-02 | 2025-03-02
[5 empty] | 2025-03-03 | 2025-03-03
[5 empty] | 2025-03-04 | 2025-03-04
|  |  | Activity Photos | List | 2025-03-05 | 2025-03-05 | Review | Samuel
|  |  |  | Details | 2025-03-06 | 2025-03-06 | Review | Samuel
2 | Employee | Employee | Employee | List View | 2025-03-11 | 2025-03-11 | Completed | Samuel
|  |  |  | Create Single | 2025-03-12 | 2025-03-12 |  | Samuel
|  |  |  | View Employee | 2025-03-13 | 2025-03-13 |  | Samuel
|  |  |  | Edit Employee | 2025-03-14 | 2025-03-14 |  | Samuel
|  |  |  | Update Permissions | 2025-03-15 | 2025-03-15 |  | Samuel
|  |  |  | Assign/Reassign Customer | 2025-03-16 | 2025-03-16 |  | Samuel
|  |  |  | Deactivate | 2025-03-17 | 2025-03-17 |  | Samuel
[5 empty] | 2025-03-18 | 2025-03-18
|  |  | Roles | List View | 2025-03-19 | 2025-03-19 | Completed | Omotolani
|  |  |  | Add new Role | 2025-03-20 | 2025-03-20 | Completed | Omotolani
|  |  |  | View Role | 2025-03-21 | 2025-03-21 | Completed | Omotolani
|  |  |  | Edit Role and Permission | 2025-03-22 | 2025-03-22 | Completed | Omotolani
|  |  |  | Add employee | 2025-03-23 | 2025-03-23 | Completed | Omotolani
|  |  |  | Mark as inactive | 2025-03-24 | 2025-03-24 | Completed | Omotolani
3 | Catalogue | Products | Products | List View | 2025-03-26 | 2025-03-26 | Completed | Omotolani
|  |  |  | Add Product | 2025-03-27 | 2025-03-27 |  | Agu
|  |  |  | View | 2025-03-28 | 2025-03-28 |  | Omotolani
|  |  |  | Edit | 2025-03-29 | 2025-03-29 |  | Agu
|  |  |  | Deactivate | 2025-03-30 | 2025-03-30 |  | Omotolani
|  | Brands | Brands | List View | 2025-04-01 | 2025-04-01 | Completed | Roland
|  |  |  | Add | 2025-04-02 | 2025-04-02 |  | Roland
|  |  |  | View Details | 2025-04-03 | 2025-04-03 |  | Roland
|  |  |  | Edit | 2025-04-04 | 2025-04-04 |  | Roland
|  |  |  | Deactivate | 2025-04-05 | 2025-04-05 |  | Roland
|  | Category | Category | List View | 2025-04-07 | 2025-04-07 | Completed | Daniel
|  |  |  | View | 2025-04-08 | 2025-04-08 | Pending | Daniel
|  |  |  | Edit | 2025-04-09 | 2025-04-09 | Pending | Daniel
|  |  |  | Create | 2025-04-10 | 2025-04-10 | Completed | Daniel
[5 empty] | 2025-04-11 | 2025-04-11
|  | Pricing | Pricing | View | 2025-04-12 | 2025-04-12 | Completed | Samuel
|  |  |  | Details | 2025-04-13 | 2025-04-13 |  | Samuel
|  |  |  | Update | 2025-04-14 | 2025-04-14 |  | Samuel
|  |  |  | Flat Pricing | 2025-04-15 | 2025-04-15 |  | Samuel
|  |  |  | Complex pricing | 2025-04-16 | 2025-04-16 |  | Samuel
|  |  |  | Add Pricing | 2025-04-17 | 2025-04-17 |  | Samuel
|  | Quantity Tier | Quantity Tier | List View | 2025-04-19 | 2025-04-19 | Completed | Roland
|  |  |  | Create | 2025-04-20 | 2025-04-20 | Completed | Roland
|  |  |  | View Details | 2025-04-21 | 2025-04-21 | Completed | Roland
|  |  |  | Edit | 2025-04-22 | 2025-04-22 | Completed | Roland
|  |  |  | Deactivate | 2025-04-23 | 2025-04-23 | Completed | Roland
[5 empty] | 2025-04-24 | 2025-04-24
|  | Collection | Collection | Create | 2025-04-25 | 2025-04-25 | Completed | Daniel
|  |  |  | List | 2025-04-26 | 2025-04-26 | Pending | Daniel
[5 empty] | 2025-04-27 | 2025-04-27 |  | Daniel
[5 empty] | 2025-04-28 | 2025-04-28 |  | Daniel
4 | Marketing | Promo | Promo | List | 2025-04-30 | 2025-04-30 | In progress | Rathan
|  |  |  | View Details | 2025-05-01 | 2025-05-01
[5 empty] | 2025-05-02 | 2025-05-02
[5 empty] | 2025-05-03 | 2025-05-03
5 | Finance | Payment Management | Inflow | List View | 2025-05-04 | 2025-05-04 | Completed | Omotolani
|  |  |  | View Details | 2025-05-05 | 2025-05-05 | Pending
|  |  | Outflow | List View | 2025-05-06 | 2025-05-06
|  |  |  | View Details | 2025-05-07 | 2025-05-07
|  |  | Settlement | List View | 2025-05-08 | 2025-05-08
|  |  |  | View Details | 2025-05-09 | 2025-05-09
6 | Settings | My customers | Customer Type | List View | 2025-05-13 | 2025-05-13 | Completed | Roland
|  |  |  | Details | 2025-05-14 | 2025-05-14 | Completed | Roland
|  |  |  | Create | 2025-05-15 | 2025-05-15 | Review(Bug) | Roland
|  |  |  | Update | 2025-05-16 | 2025-05-16 | Review(Bug) | Roland
Team Management
Company Details
7 | Notification | Notification | Notification | List | 2025-05-18 | 2025-05-18 | In Progress | Blessing
|  |  |  | Filter | 2025-05-18 | 2025-05-18 | In Progress | Blessing

## Sheet1
Phase | Assigned To | Application | Service Name | Start Date | End Date | Status | Resource Suggesting
Planning Phase | Dami, Anand s | MOS PWA | Customer | 2025-02-01 | 2025-02-03 | Completed
Requirement Analysis | Dami, Paul | MOS PWA, Library, SSO | Customer | 2025-02-01 | 2025-02-02 | Completed
Library setup | Dami | React Library | Customer, User | 2025-02-04 | 2025-02-06 | Completed
Progressbar(Linear, circle), Tag, TextField, Toast, Toggle, Typgraphy | Dami | React Library | Customer, User | 2025-02-07 | 2025-02-12 | Completed
Footer, Grid, Icon, Icon Button, Label, Loader, Modal, | Dami | React Library | Customer, User | 2025-02-12 | 2025-02-17 | Completed
Avatar, Alert, Badge, Button, Card, Checkbox, Dialog, Divider, | Dami | React Library | Customer, User | 2025-02-18 | 2025-02-21 | Completed
Other components not mentioned above | Dami | React Library | Customer, User | 2025-02-25 | In progress | Ongoing
Add library storybook | Dami | React Library | Customer, User | 2025-02-03 | 2025-02-04 | Completed
Library Documentations | Dami | React Library | Customer, User | 2025-02-10 | In progress | In progress
system icons | Dami | React Library | Customer, User | 2025-02-19 | In progress | In progress
Library themes (light and Dark) | Dami | React Library | Customer, User | 2025-02-20 | 2025-02-24 | Completed
Setup MOS pwa UI | Dami | React Library | Customer, User | 2025-02-01 | 2025-02-06 | Completed
Setup MOS pwa system notification | Dami | MOS PWA | Customer | 2025-02-26 | 2025-02-27 | Not started
Setup MOS pwa state management (RTKQuery, ccokie, local storage) | Dami, Omotolani | MOS PWA | Customer | 2025-02-27 | 2025-02-28 | In progress
Landing page pwa UI | Dami, Omotolani | MOS PWA | Customer | 2025-02-21 | 2025-02-25 | Completed
MOS Register Business details UI | Omotolani | MOS PWA | Customer | 2025-02-26 | 2025-03-04 | In progress
MOS Register Business Upload | Omotolani | MOS PWA | Customer | 2025-03-04 | 2025-03-04 | Completed
MOS Register Business types UI | Omotolani | MOS PWA | Customer | 2025-03-05 | 2025-03-08 | In progress
Deploy Libraries (omnijs and react) to Azure artifact | Dami | React Library | Customer, User | 2025-03-03 | In progress | In progress |  | 12th March
MOS Sidebar, topbar, footer UI | Dami, Omotolani | MOS PWA | Customer | 2025-03-03 | 2025-03-05 | Completed
MOS Change business | Dami, Omotolani | MOS PWA | Customer | 2025-03-04 | 2025-03-06 | Completed
MOS Create Employee UI | Samuel | MOS PWA | User | 2025-03-03 | 2025-03-05 | Review
MOS Employee UI List | Samuel | MOS PWA | User | 2025-03-05 | 2025-03-10 | Completed
MOS Employee UI List (my employees, upload history) | Samuel | MOS PWA | User | 2025-03-05 | 2025-03-10 | In progress
MOS Employee UI List Filter | Samuel | MOS PWA | User | 2025-03-06 | 2025-03-10 | In progress
MOS Employee Roles UI List | Samuel,Agu | MOS PWA | User | 2025-03-10 | 2025-03-13 | Not started
MOS Employee UI List Details (Performance metrics, Tasks and targets, beat plan, activity photos, Audit log) | Samuel | MOS PWA | User | 2025-03-12 | 2025-03-18 | Not started
MOS Employee UI List Update Employee | Samuel | MOS PWA | User | 2025-03-14 | 2025-03-18 | In progress
MOS Employee UI List Update Permission | Samuel | MOS PWA | User | 2025-03-11 | 2025-03-14 | In progress
MOS Employee Manage Omniforce request | Samuel | MOS PWA | User |  |  | In progress
MOS Employee Add Employee by single UI | Dami, Samuel | MOS PWA | User |  |  | Completed
MOS Employee Add Employee by bulk | Dami, Samuel | MOS PWA | User |  |  | Not started
MOS Employee Add Employee ERP integration | Samuel | MOS PWA | User |  |  | Not started
MOS Employee Employee Activate | Samuel | MOS PWA | User |  |  | Not started
MOS Employee Employee Export | Samuel | MOS PWA | User |  |  | Not started
Setup SSO | Dami,Paul | SSO | Customer | 2025-02-27 | 2025-02-28 | Ongoing | Agu
SSO Login UI Landing page | Dami | SSO | User | 2025-02-28 | 2025-03-03 | In progress
SSO Login type UI | Dami | SSO | User | 2025-03-03 | 2025-03-05 | In progress
SSO registration UI Landing page | Dami | SSO | User | 2025-03-04 | 2025-03-07 | In progress
SSO Alert and toast UI | Dami | SSO | User | 2025-03-07 | 2025-03-08 | In progress
SSO Reset Password UI | Dami | SSO | User | 2025-03-10 | 2025-03-12 | Not started
SSO Complete registration UI | Paul | SSO | User | 2025-03-12 | 2025-03-13 | Not started
MOS Getting started page | Omotolani | MOS PWA | Customer | 2025-03-12 | 2025-03-13 | Completed
MOS settings Landing UI | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
MOS Customer Management UI | Roland | MOS PWA | Customer | 2025-03-17 | 2025-03-14 | Not started | Samuel & 5
MOS Customer List (table view) UI | Roland, Dami | MOS PWA | Customer | 2025-03-14 | 2025-03-15 | Completed
MOS Customer List (map view) UI | Roland, Dami | MOS PWA | Customer | 2025-03-15 | 2025-03-16 | Not started
MOS Customer View profile | Agu | MOS PWA | Customer | 2025-03-15 | 2025-03-16 | Completed
MOS Customer Reassign Agent | Agu | MOS PWA | Customer | 2025-03-15 | 2025-03-16 | Completed
MOS CustomerBrands | Agu | MOS PWA | Customer | 2025-03-15 | 2025-03-16 | Completed
MOS Customer Customer Location | Agu | MOS PWA | Customer | 2025-03-15 | 2025-03-16 | Not started
MOS Customer Sub contact | Agu | MOS PWA | Customer | 2025-03-15 | 2025-03-16 | Not started
MOS Customer Deactivate | Agu | MOS PWA | Customer | 2025-03-15 | 2025-03-16 | Completed
MOS add new customer | Roland | MOS PWA | Customer | 2025-03-16 | 2025-03-17 | Completed
MOS add new customer OTP verification | Roland | MOS PWA | Customer | 2025-03-17 | 2025-03-18 | Not started
MOS complete add customer | Roland | MOS PWA | Customer | 2025-03-18 | 2025-03-19 | Completed
MOS Complete add customer location | Roland | MOS PWA | Customer | 2025-03-19 | 2025-03-20 | Not started
MOS Create Single Customer UI | Roland | MOS PWA | Customer | 2025-03-20 | 2025-03-21 | Completed
MOS Create multiple Customer UI | Roland | MOS PWA | Customer | 2025-03-21 | 2025-03-22 | Not started
MOS Create Customer Type UI | Roland | MOS PWA | Customer | 2025-03-22 | 2025-03-23 | Not started
MOS List Customer Type UI | Roland | MOS PWA | Customer | 2025-03-14 | 2025-03-14 | Completed
MOS customer type segments UI | Samuel | MOS PWA | Customer | 2025-03-24 | 2025-03-25 | Not started
MOS customer type setup UI | Samuel | MOS PWA | Customer | 2025-03-25 | 2025-03-26 | Not started
MOS customer type setup specific segment UI | Samuel | MOS PWA | Customer | 2025-03-26 | 2025-03-27 | Not started
MOS customer type setup specific customer type UI | Agu | MOS PWA | Customer | 2025-03-27 | 2025-03-28 | Not started
MOS view customer types (details) | Roland | MOS PWA | Customer | 2025-03-28 | 2025-03-29 | Completed
MOS Edit customer type | Roland | MOS PWA | Customer | 2025-03-29 | 2025-03-30 | Completed
MOS Deactivate customer type) | Roland | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
MOS Permissions | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Add permissions per modules | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
MOS Create a team | Agu | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Not started
MOS List Roles | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Create roles | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Review
List Categories | Samuel | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Review
Create Categories | Roland | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Review
Productivity Tracker (Plan) List | Blessing | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Productivity Tracker (Plan) Create | Blessing | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Productivity Tracker (Plan) Details | Blessing | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Productivity Tracker (Targets) List | Howard | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Productivity Tracker (Targets) Create | Howard | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Productivity Tracker (Targets) Details | Howard | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Productivity Tracker (Map Overlay) | Blessing | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Productivity Tracker (Activity Photos) | Howard | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | In progress
Product List | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Product Create | Agu | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Product Details | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Pricing List | Samuel | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Pricing Details | Samuel | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Pricing Update | Samuel | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Finance Payment Module | Omotolani | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Notifications | Agu | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Help & Support | Samuel | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Location | Roland | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Report | Kumar | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Inventory | Howard | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Promo | Howard | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Report | Blessing | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Collection | Resource 9 | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Form Builder | Resource 10 | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Order Processing | Resource 11 | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Report | Resource 12 | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed
Settings | Resource 13 | MOS PWA | Customer | 2025-03-30 | 2025-03-31 | Completed